THE VTF COLLECTIVE

Uncompromised — Your Author Timeline

A quick overview of what happens and when

Here is the path from acceptance to launch day. Please treat the dates below as firm, since the whole book depends on every author staying on schedule.

| Date | What's happening | What you need to do |
| --- | --- | --- |
| Sep 28, 2026 | Call for authors opens | Complete the interest form. |
| Oct 23, 2026 | Applications close | Submit your interest form and story summary by this date. |
| By Oct 30, 2026 | Acceptance notices sent | Watch your inbox (and spam folder). |
| Nov 6, 2026 | Lineup locked | Return your signed agreement, pay your Seat Price, and send your bio, headshot, and social handles. |
| Nov 16, 2026 | First drafts due | Submit the full first draft of your story. |
| Nov 17 – Dec 10, 2026 | Editing and revisions | Receive editorial notes by Nov 30, revise, and return your piece by Dec 10. |
| Dec 18, 2026 | Final piece sign-off | Approve your final edited piece. This is your last chance for changes. |
| Dec 21, 2026 – Jan 20, 2027 | Compilation, copyedit, and design | No action needed. We assemble and design the book. |
| Jan 21 – Feb 1, 2027 | Proof review | Review your pages and send corrections within the window. |
| Feb 1 – Feb 17, 2027 | Pre-orders and printing | Share the cover reveal and pre-order link with your network. |
| Feb 20, 2027 | Publication and Launch Party | Celebrate, and share the launch far and wide. |

Timeline is subject to change with written notice. Questions? Email info@thevtfcollective.com.